# Warehouse Automation Rollout

This plan covers the phased rollout of the new pick-and-pack automation across the three regional warehouses.

# Phase 1: North Warehouse

Installation begins the first week of Q4, with staff training running in parallel during the second week.

Conveyor belt replacement

Barcode scanner upgrade

Staff certification (2 days per shift)

# Phase 2: South and West Warehouses

Rollout follows six weeks after North, once lessons learned from Phase 1 are folded into the installation checklist.

# Risks

The main risk is parts lead time: conveyor motors currently run an eight week order-to-delivery window.